## TemplateDoHistorico - Model Nam
Model Name and Version - Agent Name - Skills and Agents
Prompt | Issues | Overall result | Overall sentiment | Observations
Implement the smallest possible backend slice for closed questions by exposing GET /questions with in-memory data only, without touching the frontend. | No automated acceptance harness existed yet; validation of the endpoint behavior was initially manual. The implementation was intentionally minimal and concentrated in one backend file. | Accepted | Useful | Copilot respected the scope well and delivered a minimal backend-only slice aligned with the prompt. The endpoint returned the expected JSON structure and did not expand into CRUD, persistence, or frontend changes. Follow-up validation was still needed to confirm build/test evidence.
Inspect existing server scripts and run only the current validation commands to confirm build/check/test evidence for iteration 1A, without changing the feature implementation. | Automated tests for this slice do not exist yet; the current test script is only a placeholder. Validation evidence had to rely on build/check plus endpoint smoke test. | Accepted | Useful | This follow-up did not expand scope and clarified the real validation state of the backend. check passed, build passed, the endpoint still responded correctly, and the absence of real automated tests was made explicit. It improved monitoring quality without changing product behavior.
Implement the smallest possible frontend slice to fetch GET /questions and display closed questions with basic loading and error states, without adding create/edit/delete or unrelated architecture. | Validation still depended on manual checks for loading and error states. The UI was minimal and visually rough, but this was acceptable because styling was intentionally out of scope for this iteration. | Accepted | Useful | Copilot respected the scope and delivered a minimal frontend slice that consumed GET /questions, rendered question statements and alternatives, and included basic loading and error handling. The iteration stayed focused and did not expand into create/edit/delete or other features.
You are working on a university assignment repository. Repository context: - React + TypeScript client in `sistema/client` - Node + TypeScript server in `sistema/server` - Gherkin/Cucumber scenarios in `sistema/features` - Iteration 1A is already accepted and committed - Iteration 1B is already accepted and committed - This iteration must be the smallest possible vertical slice for closed-question creation Goal of this iteration: Implement only the minimum necessary to create a closed question and make it appear in the visible list. Business scope for this iteration: - A question has: - `statement` - exactly 4 alternatives - Each alternative has: - `text` - `isCorrect` - Storage must remain in memory only - Frontend must provide a minimal form - After successful creation, the visible question list must refresh or update - Show a simple validation message when required fields are missing Strict scope control: - Prefer tiny, localized changes - Reuse the current structure from iterations 1A and 1B - Reuse the current question list screen instead of creating new routing/pages - Do not introduce database, persistence layer, or extra architecture - Do not redesign the UI - Do not broad-refactor unrelated code Likely files to change should stay close to: - `sistema/server/src/server.ts` - `sistema/client/src/App.tsx` - `sistema/features/question-creation.feature` Avoid creating extra files unless strictly necessary. Out of scope: - edit question - delete question - dynamic number of alternatives - exam management - PDF generation - CSV generation - grading/correction - authentication - routing changes - broad refactoring - database persistence Assumptions to use unless the code clearly requires a smaller equivalent: - Backend request body for `POST /questions`: { "statement": "string", "alternatives": [ { "text": "string", "isCorrect": true }, { "text": "string", "isCorrect": false }, { "text": "string", "isCorrect": false }, { "text": "string", "isCorrect": false } ] } - Response may return the created object, preferably with an `id` - Validation can be minimal and server-side + client-side - The frontend can use checkboxes or another minimal boolean control for correctness A minimal feature file for this iteration already exists at `sistema/features/question-creation.feature`; update that file if needed instead of creating a different one. Before editing: 1. Summarize the implementation plan in a few lines 2. List the likely files to change 3. State the chosen request/response shape 4. Mention brief risks 5. State the stop condition explicitly Also create or update a minimal Gherkin feature for this iteration with at least these scenarios: - successful creation of a closed question with 4 alternatives - failed submission when required fields are missing Acceptance criteria: - server build still passes - server type check/check still passes - client build still passes - backend exposes `POST /questions` - backend stores created questions in memory - frontend displays a minimal create-question form - user can fill statement + 4 alternatives + correctness flags - submitting valid data creates a question - the newly created question appears in the visible list - submitting missing required data shows a simple validation message - no unrelated files are changed Implementation guidance: - Keep the backend change minimal: add `POST /questions` near the current in-memory questions flow - Keep the frontend change minimal: add a small form near the current list flow - Do not implement dynamic add/remove of alternatives - Do not create extra pages - Do not implement advanced validation rules - Do not continue after the vertical slice works After editing: 1. Explain exactly what changed 2. List all changed files 3. Explain how to validate locally 4. Explicitly list what remains out of scope 5. Confirm the stop condition was respected Stop condition: Stop immediately after a question can be created through the frontend and appears in the visible list. Do not continue into edit/delete, exam management, PDF, CSV, grading, or database persistence. | The first generated version left the seed questions with only three alternatives, which was inconsistent with the iteration rule of exactly four alternatives per question. A small adjustment was required before final acceptance. Validation also depended on manual checks for valid and invalid form submission. | Accepted partially | Useful | Copilot stayed close to the requested scope and implemented a minimal closed-question creation flow without expanding into edit/delete, dynamic alternatives, or extra architecture. The backend validation and frontend form were both simple and aligned with the iteration goal. A small manual correction was needed to keep the seeded question model consistent with the “exactly four alternatives” rule.
You are working on a university assignment repository. Repository context: - React + TypeScript client in `sistema/client` - Node + TypeScript server in `sistema/server` - Gherkin/Cucumber scenarios in `sistema/features` - Iterations 1A, 1B and 1C are already accepted and committed - This iteration must be the smallest possible vertical slice for closed-question removal - There is also repository guidance in `.github/copilot-instructions.md`; follow it Goal of this iteration: Implement only the minimum necessary to remove an existing closed question and make it disappear from the visible list. Business scope for this iteration: - Backend must expose `DELETE /questions/:id` - Storage remains in memory only - Frontend must provide a minimal remove action for each visible question - After successful removal, the visible question list must refresh or update - Show a simple user-visible error message if removal fails Strict scope control: - Prefer tiny, localized changes - Reuse the current structure from iterations 1A, 1B and 1C - Reuse the current question list screen instead of creating new routing/pages - Do not introduce persistence or extra architecture - Do not redesign the UI - Do not broad-refactor unrelated code - Do not implement any functionality beyond this removal slice Likely files to change: - `sistema/server/src/server.ts` - `sistema/client/src/App.tsx` - `sistema/features/question-removal.feature` Assumptions to use unless the code clearly requires a smaller equivalent: - Questions already have an `id` - `DELETE /questions/:id` may return `204` on success - On failure, the backend may return a simple error status such as `404` or `500` - Frontend can use a simple button labeled `Remove` - Error handling can be minimal and user-visible Chosen request/response shape: - Request: `DELETE /questions/:id` - Success response: prefer `204 No Content` - Failure response: simple JSON error payload is acceptable, such as `{ "message": "Unable to remove question" }` Before editing: 1. Summarize the implementation plan in a few lines 2. List the likely files to change 3. State the chosen request/response shape 4. Mention brief risks 5. State the stop condition explicitly Gherkin requirement: - Reuse and update `sistema/features/question-removal.feature` if needed - Keep at least these scenarios represented: - successful removal of an existing closed question - failed removal request with a simple user-visible error Acceptance criteria: - server check still passes - server build still passes - client build still passes - backend exposes `DELETE /questions/:id` - backend removes the target question from memory - frontend displays a minimal remove action for each visible question - removing an existing question makes it disappear from the visible list - a failed removal shows a simple error message - no unrelated files are changed Implementation guidance: - Keep the backend change minimal: add `DELETE /questions/:id` near the current in-memory questions flow - Keep the frontend change minimal: add a small remove button near the current list flow - Reuse existing state and fetching logic whenever possible - Do not add confirmation modals - Do not create extra pages - Stop as soon as the vertical slice works After editing: 1. Explain exactly what changed 2. List all changed files 3. Explain how to validate locally 4. Point out any risks or limitations that remain 5. Confirm the stop condition was respected Stop condition: Stop immediately after a question can be removed from the frontend and disappears from the visible list. Do not continue into any other feature. | The iteration worked functionally, including successful and failed removal flows, but the implementation kept concentrating responsibilities in App.tsx instead of moving toward a more modular frontend structure. This did not break the scope of the iteration, but it reduced code organization quality. The Gherkin feature file also continued to serve only as acceptance guidance, since the repository still lacks executable Cucumber step definitions. | Accepted partially | Useful | Copilot stayed close to the requested scope and implemented a minimal closed-question removal slice. The backend added DELETE /questions/:id with in-memory removal, and the frontend added a simple Remove action that updated the visible list and showed a basic user-visible error when deletion failed. The iteration worked correctly in manual testing, but the implementation continued to centralize frontend responsibilities in App.tsx instead of improving modularity. This was acceptable for the minimal slice, but it remains a quality concern for future iterations.
You are working on a university assignment repository. Repository context: - React + TypeScript client in `sistema/client` - Node + TypeScript server in `sistema/server` - Gherkin/Cucumber scenarios in `sistema/features` - Iterations 1A, 1B, 1C and 1D are already accepted and committed - This iteration must be the smallest possible vertical slice for closed-question editing - There is also repository guidance in `.github/copilot-instructions.md`; follow it Goal of this iteration: Implement only the minimum necessary to edit an existing closed question and make the updated data appear in the visible list. Business scope for this iteration: - Backend must expose `PUT /questions/:id` - Storage remains in memory only - Frontend must provide a minimal edit action for an existing visible question - The user must be able to edit: - statement - the same 4 alternatives - correctness flags - After successful editing, the visible question list must refresh or update - Show a simple user-visible validation message if required fields are missing Strict scope control: - Prefer tiny, localized changes - Reuse the current structure from iterations 1A, 1B, 1C and 1D - Reuse the current question list screen instead of creating new routing/pages - Do not introduce persistence or extra architecture - Do not redesign the UI - Do not broad-refactor unrelated code - Do not implement any functionality beyond this editing slice - If the current UI logic is concentrated in `App.tsx`, do not refactor it broadly in this iteration - Only extract code if the existing repository already clearly uses a split structure and the equivalent smaller change fits better there Likely files to change: - `sistema/server/src/server.ts` - `sistema/client/src/App.tsx` - `sistema/features/question-editing.feature` Assumptions to use unless the code clearly requires a smaller equivalent: - Questions already have an `id` - `PUT /questions/:id` may accept: { "statement": "string", "alternatives": [ { "text": "string", "isCorrect": true }, { "text": "string", "isCorrect": false }, { "text": "string", "isCorrect": false }, { "text": "string", "isCorrect": false } ] } - Success response may return the updated question - Failure response may return a simple JSON error payload - Frontend can reuse a very simple inline edit mode or temporary edit state in the existing screen - Validation can stay minimal and user-visible Chosen request/response shape: - Request: `PUT /questions/:id` - Success response: updated question JSON - Failure response: simple JSON error payload Before editing: 1. Summarize the implementation plan in a few lines 2. List the likely files to change 3. State the chosen request/response shape 4. Mention brief risks 5. State the stop condition explicitly Gherkin requirement: Create or update `sistema/features/question-editing.feature` with at least these scenarios: - successful editing of an existing closed question - failed submission when required fields are missing Suggested Gherkin shape: Feature: Editing closed questions Scenario: Successfully edit an existing closed question Given an existing closed question is available When the user edits its statement, alternatives, and correctness flags And saves the changes Then the system updates the question And the visible list shows the updated data Scenario: Prevent invalid edit submission Given the user is editing an existing closed question When required fields are missing And the user tries to save Then the system shows a simple validation message And the question is not updated Acceptance criteria: - server check still passes - server build still passes - client build still passes - backend exposes `PUT /questions/:id` - backend updates the target question in memory - frontend displays a minimal edit action for a visible question - editing statement/alternatives/correctness updates the visible list - invalid edit submission shows a simple validation message - no unrelated files are changed Implementation guidance: - Keep the backend change minimal: add `PUT /questions/:id` near the current in-memory questions flow - Keep the frontend change minimal: add a very small edit flow near the current list flow - Reuse existing state and form logic whenever possible - Do not add modals or extra pages - Do not add persistence - Do not start architectural cleanup in this iteration - Stop as soon as the vertical slice works After editing: 1. Explain exactly what changed 2. List all changed files 3. Explain how to validate locally 4. Point out any risks or limitations that remain 5. Confirm the stop condition was respected Stop condition: Stop immediately after a question can be edited from the frontend and the updated data appears in the visible list. Do not continue into any other feature. | The iteration stayed within scope and worked functionally, but validation evidence was initially concentrated on builds and direct API tests. The frontend edit flow remained centralized in App.tsx, which matches the prompt constraints for a minimal slice but still leaves a maintainability concern for future iterations. The Gherkin file also continued to act only as acceptance guidance because the repository still lacks executable Cucumber step definitions. | Accepted | Useful | Validation was completed through build results, direct endpoint testing, and manual UI verification of both valid and invalid edit flows.
You are working on a university assignment repository. Repository context: - React + TypeScript client in `sistema/client` - Node + TypeScript server in `sistema/server` - Gherkin/Cucumber scenarios in `sistema/features` - Iterations 1A, 1B, 1C, 1D and 1E are already accepted and committed - This iteration must close the questions block before moving into exams - There is repository guidance in `.github/copilot-instructions.md`; follow it Iteration goal: Consolidate the Gherkin files for the questions block and create the initial executable Cucumber-JS structure for those scenarios, without expanding into browser automation or other system phases. Important ambiguity to resolve correctly: - The user prefers “more automation” - But this iteration still must NOT become full browser automation - So implement the maximum automation that stays inside a minimal Cucumber-JS scaffold in `sistema/server` - Do not add Cypress, Playwright, or exam/PDF/CSV/grading behavior Business scope for this iteration: - Normalize the question-related `.feature` files under `sistema/features` - Keep exactly one `Feature` per `.feature` file - Keep the files strictly question-scoped - Add the initial Cucumber-JS setup in `sistema/server` - Add an npm script to run only the question-related feature files - Add the initial step-definition/support structure for future acceptance tests - Bind the current question scenarios to an initial runnable Cucumber structure - Keep everything small, localized, and reversible Strict scope control: - Do not implement exam features - Do not add browser automation frameworks - Do not add Cypress - Do not add Playwright - Do not refactor client or server architecture broadly - Do not introduce PDF, CSV, correction, reports, or unrelated features - Do not create a giant generic test framework - Stop as soon as the question block has normalized feature files and an executable initial Cucumber-JS scaffold Likely files to change: - `sistema/features/question-listing-frontend.feature` - `sistema/features/question-creation.feature` - `sistema/features/question-removal.feature` - `sistema/features/question-editing.feature` - `sistema/server/package.json` - `sistema/server/bdd/step-definitions/questions.steps.js` - `sistema/server/bdd/support/world.js` - `sistema/server/bdd/support/hooks.js` Implementation guidance: - Keep one Feature per file - Keep the wording consistent across question scenarios - Add `@cucumber/cucumber` as a dev dependency in `sistema/server` - Add a script similar to: `bdd:questions: cucumber-js ../features/question-*.feature --require ./bdd/step-definitions/**/*.js --require ./bdd/support/**/*.js` - Create only the minimal support files needed - Prefer a small shared World/state object rather than a broad framework - Avoid adding extra dependencies unless absolutely necessary - Do not simulate real browser behavior - If some scenarios are frontend-oriented, keep them represented at the acceptance-spec level without introducing browser tooling - Make the resulting command runnable and deterministic Before editing: 1. Summarize the implementation plan in a few lines 2. List the likely files to change 3. State clearly what will be executable after this iteration 4. State clearly what will NOT be automated after this iteration 5. Mention risks 6. State the stop condition explicitly Acceptance criteria: - question-related `.feature` files are normalized and remain question-scoped - each `.feature` file contains a single `Feature` - `@cucumber/cucumber` is added as a dev dependency in `sistema/server` - an npm script exists to run the question-related Cucumber features - initial `bdd/step-definitions` and `bdd/support` structure exists in `sistema/server` - the question BDD command runs locally - no unrelated system features are changed - no exam/PDF/CSV/correction work is introduced After editing: 1. Explain exactly what changed 2. List all changed files 3. Explain how to validate locally 4. Point out remaining limitations honestly 5. Confirm the stop condition was respected Stop condition: Stop immediately after: - the question `.feature` files are normalized, - the initial Cucumber-JS structure exists, - the question BDD npm script runs, - and the iteration remains fully inside the questions block. Do not continue into exams, PDF, CSV, grading, Cypress, Playwright, or full browser automation. | This iteration created an initial executable Cucumber-JS scaffold for the questions block, but the scenarios still run against an in-memory Cucumber world instead of the real React/Node application flow. This is acceptable for an initial BDD structure, but integrated acceptance coverage is still limited. | Accepted | Useful | Copilot stayed within the intended scope of the questions Gherkin/Cucumber consolidation step. The question-related feature files were normalized and kept domain-focused, the server package gained @cucumber/cucumber and a dedicated bdd:questions script, and an initial step-definition/support structure was created. The setup is now enough to execute a first BDD scaffold for the questions block. A remaining limitation is that the current steps operate on an in-memory Cucumber world instead of exercising the real frontend/backend application flow.
You are working on a university assignment repository. Repository context: - React + TypeScript client in `sistema/client` - Node + TypeScript server in `sistema/server` - Gherkin/Cucumber scenarios in `sistema/features` - The questions block is already completed and committed - This iteration must be the smallest possible backend slice for exam listing - There is also repository guidance in `.github/copilot-instructions.md`; follow it - The Gherkin scenarios for this iteration already exist in: `sistema/features/exam-listing.feature` Goal of this iteration: Implement only the minimum necessary backend slice to list exams. Business scope for this iteration: - Add an in-memory exam structure - Expose `GET /exams` - Return a JSON array from memory - Each exam should have at least: - `id` - `title` - `answerMode` - `answerMode` can initially be one of: - `letters` - `powersOfTwo` Existing acceptance scenarios: Feature: Exam listing Scenario: List existing exams Given the server is running When I request the list of exams Then the response should be successful And the response body should be a JSON array of exams Scenario: Exam items include basic metadata Given the server is running When I request the list of exams Then each exam should include an id And each exam should include a title And each exam should include an answer mode Strict scope control: - Prefer tiny, localized changes - Reuse the current backend structure - Do not touch the frontend in this iteration - Do not introduce persistence or extra architecture - Do not broad-refactor unrelated code - Do not implement creation, editing, deletion, PDF, CSV, grading, or question selection - Do not add extra exam fields unless strictly necessary - Do not change the feature file unless there is a real mismatch with the existing backend test structure - Prefer reusing the same BDD step-definition pattern already used by the questions block Likely files to change: - `sistema/server/src/server.ts` - existing backend files already used for in-memory routes/types, if any - existing Cucumber step-definition/support files for server acceptance tests, if needed Chosen response shape: - `GET /exams` must return HTTP 200 - response body must be a JSON array - each item must look like: { "id": "exam-1", "title": "Example Exam", "answerMode": "letters" } Assumptions: - In-memory storage is acceptable - Seed data with one or two example exams is acceptable for this iteration - If there is already a shared pattern for route registration or in-memory data, reuse it instead of creating a new architecture layer Before editing: 1. Summarize the implementation plan in a few lines 2. List the likely files to change 3. State the chosen response shape 4. Mention brief risks 5. State the stop condition explicitly Acceptance criteria: - server build still passes - server check still passes - backend exposes `GET /exams` - `GET /exams` returns HTTP 200 - response is a JSON array - each exam has `id`, `title`, and `answerMode` - `answerMode` is either `letters` or `powersOfTwo` - the existing `exam-listing.feature` scenarios pass - no frontend changes are made - no unrelated files are changed Implementation guidance: - Keep the change minimal - Add `GET /exams` near the current in-memory backend flows - Reuse the existing backend and BDD conventions from the questions block - Only add step definitions/support code if the new feature is not already wired - Do not implement POST/PUT/DELETE for exams - Stop as soon as the endpoint works and returns the expected structure After editing: 1. Explain exactly what changed 2. List all changed files 3. Explain how to validate locally 4. Point out remaining limitations 5. Confirm the stop condition was respected Stop condition: Stop immediately after `GET /exams` works and returns the expected in-memory list and the current exam listing scenarios can pass. Do not continue into frontend, exam creation, question selection, PDF, CSV, or grading. | The iteration stayed within scope and worked as intended, but the BDD step-definition file remains shared and still uses the name questions.steps.js even after adding exam-listing coverage. This does not break the slice, but it slightly reduces clarity of test organization. | Accepted | Useful | Copilot stayed close to the requested scope and implemented the smallest backend slice for exam listing. The backend gained an in-memory exam structure and a GET /exams endpoint returning a JSON array with id, title, and answerMode. The existing BDD scaffold was reused to cover the exam-listing scenarios, and validation passed through server build/check plus cucumber execution of the feature. No frontend or unrelated system features were changed.
Perform a minimal frontend modularization so the project can grow without concentrating too much logic in App.tsx. Keep the current behavior unchanged and only extract types, services, and basic components. | No blocking issue, but the modularization is still shallow. App.tsx still keeps most state and form logic; QuestionList became prop-heavy; API URL is still hardcoded; validation evidence was mostly build-based and should be complemented with manual smoke testing. | Accepted | Useful | The agent respected the scope and did not introduce new business features. It extracted shared types, moved question fetch logic to a service file, and separated list rendering into a basic component. This reduced responsibility concentration in App.tsx, although the architecture is still only minimally improved.
You are working on a university assignment repository. Repository context: - React + TypeScript client in `sistema/client` - Node + TypeScript server in `sistema/server` - Gherkin/Cucumber scenarios in `sistema/features` - Iteration 2A is already accepted and committed - Iteration 2B.1 (minimal client modularization) is already accepted and committed - There is repository guidance in `.github/copilot-instructions.md`; follow it Goal of this iteration: Implement the smallest possible frontend slice to fetch `GET /exams` and display exams already provided by the backend. Important implementation constraints: - Keep this iteration small and verifiable - Preserve and reinforce the modularization introduced in Iteration 2B.1 - Do not concentrate the full implementation in `App.tsx` - Prefer dedicated files for type, service, and rendering component - Reuse existing modular structure if types/services/components folders already exist - If `App.tsx` is still used, keep it only as a composition/root file as much as possible Existing acceptance scenarios: There is already a feature file at: - `sistema/features/exam-listing-frontend.feature` It contains these scenarios: - Display exams loaded from backend - Display error when exam loading fails Use that file as the behavioral contract for this iteration. Do not expand scope beyond those scenarios unless a tiny adjustment is strictly necessary for consistency. What this iteration must do: - Fetch `GET /exams` from the backend when the exams screen loads - Render a list of exams - Show each exam title - Show each exam answerMode - Show a simple loading state - Show a simple error state Expected response shape assumption: Assume `GET /exams` returns an array of exam objects and each exam has at least: - `id` - `title` - `answerMode` If the current backend shape differs, inspect the existing backend implementation and adapt the frontend to the real response shape with the smallest possible change. Do not change backend behavior unless absolutely necessary. Preferred minimal modularization: - dedicated exam type file - dedicated exams service file for HTTP fetching - dedicated UI component for exam list rendering - optional small item component only if it keeps changes cleaner without broadening scope Likely files to change: - `sistema/client/src/App.tsx` - `sistema/client/src/types/exam.ts` - `sistema/client/src/services/exams.ts` - `sistema/client/src/components/ExamList.tsx` - optionally `sistema/client/src/components/ExamListItem.tsx` - `sistema/features/exam-listing-frontend.feature` only if a tiny consistency fix is required Out of scope: - POST /exams - edit/delete exams - question selection for exams - routing changes - exam creation screen/form - redesign - unrelated refactors - touching question features - PDF generation - CSV generation - grading/correction Acceptance criteria: - frontend fetches `GET /exams` - UI renders a list of exams - each exam displays `title` - each exam displays `answerMode` - loading state exists - error state exists - client build passes - backend remains working - implementation stays modular - no unrelated files are changed - no exam creation functionality is added Before editing: 1. summarize the implementation plan briefly 2. list the files you expect to change 3. state the assumption about `GET /exams` response shape 4. mention the main risk briefly 5. state the stop condition explicitly After editing: 1. explain exactly what changed 2. list all changed files 3. explain how to validate locally 4. explicitly confirm what stayed out of scope 5. confirm the stop condition was respected Stop condition: Stop immediately after the frontend successfully displays exams loaded from `GET /exams` with basic loading and error states. Do not continue into exam creation, editing, deletion, routing, or any other feature. | The iteration improved modularity by introducing dedicated exam type, service, and list component files, and it successfully displayed exams from GET /exams. However, App.tsx still keeps global loading/error returns for the questions flow, which can interfere with the independent loading/error behavior of the exam listing. This means the exam feature is functionally present but not yet fully isolated in the UI composition. | Accepted partially | Useful | Copilot stayed close to the intended scope and implemented a modular frontend slice for exam listing. The iteration introduced a dedicated Exam type, a service for GET /exams, and an ExamList component for rendering title and answerMode. This improved separation compared to keeping all new logic in App.tsx. However, App.tsx still contains global loading/error returns tied to the question flow, which can prevent the exam component from independently expressing its own loading and error states. Because of that, the iteration is functionally correct but still has a UI composition limitation.
Corrective iteration for 2B.2: decouple exam listing from question loading/error with minimal localized change. | Initial implementation had exam loading inside App.tsx and exam rendering could be blocked by question loading/error. | Accepted | Useful | The correction created ExamSection, moved exam state and fetch logic out of App.tsx, and allowed the exam list to render independently from the questions flow. Build passed and the iteration became acceptable after correction.
Create the minimum exam creation flow with title and answerMode, storing data in memory and updating the visible frontend list. | Goal achieved, but no evidence of Gherkin execution and some responsibility concentration remained in ExamSection.tsx and server.ts. | Accepted partially | Useful | Functional delivery, with moderate technical debt for future growth.
You are working on a university assignment repository. Repository context: - React + TypeScript client in `sistema/client` - Node + TypeScript server in `sistema/server` - Gherkin/Cucumber scenarios in `sistema/features` - Iterations 2A, 2B and 2C are already accepted and committed - There is repository guidance in `.github/copilot-instructions.md`; follow it Working mode: Treat the remaining exams block as a sequence of small internal subparts. Do NOT implement everything in one pass. After each subpart, stop and explain: 1. what changed 2. which files changed 3. how I should validate locally 4. what remains for the next subparts Do not continue automatically after a subpart. I will review, record history, and commit before asking you to continue. Overall goal: Finish the remaining exams block by covering: - linking existing questions to an exam - completing exam update/removal - consolidating Gherkin/Cucumber coverage for exams Important note: `answerMode` already exists in the exam model and creation flow. Do not treat it as a separate large feature. Preserve and support it consistently during linking, editing, and BDD coverage. State the implementation plan before coding: - summarize all subparts - list likely files per subpart - say what you will do in Subpart 1 only - mention brief risks - state the stop condition explicitly Subpart 1 — Link questions to an existing exam Goal: - allow selecting existing question ids for an existing exam - store `questionIds` in memory - update the visible exam data after save Suggested Gherkin intent: Scenario: Link existing questions to an existing exam Acceptance criteria: - backend supports updating exam questionIds in memory - frontend allows selecting existing questions for an exam - saving updates the visible exam data - `server check` passes - `server build` passes - `client build` passes - no unrelated files are changed Stop condition for Subpart 1: Stop as soon as linking questionIds works end-to-end. Do not implement title editing, answerMode editing, deletion, or feature consolidation yet. Subpart 2 — Complete exam editing Goal: - allow editing `title` - allow editing `answerMode` - allow editing `questionIds` Suggested Gherkin intent: Scenario: Edit an existing exam Acceptance criteria: - backend supports updating title, answerMode, and questionIds - frontend allows editing those values minimally - updated exam appears correctly in the visible list - `server check` passes - `server build` passes - `client build` passes Stop condition for Subpart 2: Stop as soon as minimal editing works end-to-end. Do not implement deletion or BDD consolidation yet. Subpart 3 — Remove exams Goal: - implement minimal exam deletion Suggested Gherkin intent: Scenario: Remove an existing exam Acceptance criteria: - backend exposes DELETE /exams/:id - removing an exam removes it from memory - frontend shows a minimal remove action - removed exam disappears from the visible list - failed removal shows a simple error message - `server check` passes - `server build` passes - `client build` passes Stop condition for Subpart 3: Stop as soon as deletion works end-to-end. Do not implement BDD consolidation yet. Subpart 4 — Exams Gherkin/Cucumber consolidation Goal: - create or normalize `sistema/features/exam-management.feature` - consolidate exam-related scenarios there - cover: - minimal exam creation already implemented - linking questions to an exam - editing an exam - removing an exam - answerMode consistency where relevant Important BDD rule: Prefer `sistema/features/exam-management.feature` as the final consolidated feature file for the exams block. Avoid leaving confusing duplicate exam scenarios across multiple feature files. Acceptance criteria: - `sistema/features/exam-management.feature` exists and is normalized - exam-related step coverage is added or updated minimally - existing BDD scripts still run - no unrelated blocks are changed Strict scope control: - keep each subpart minimal - stop after each subpart - do not continue automatically - do not introduce persistence - do not introduce PDF, CSV, grading, or later blocks - do not redesign the UI - do not broad-refactor unrelated code - do not create new routes/pages unless strictly necessary Modularity expectation: - avoid forcing all logic into one file when a small extraction is justified - prefer small, maintainable changes - avoid heavy architecture Likely files across the sequence: - `sistema/server/src/server.ts` - `sistema/client/src/types/exam.ts` - `sistema/client/src/services/exams.ts` - current exam-related frontend components/sections - `sistema/features/exam-management.feature` - exam-related step-definition/support files if needed Implementation rule: Start with Subpart 1 only. After finishing Subpart 1, stop and explain exactly what changed, how to validate it, and what remains for Subparts 2–4. Do not implement Subparts 2–4 yet. | The agent was useful for accelerating implementation, but it did not fully preserve alignment between reported progress and actual behavior. Manual validation found important problems: exam deletion was still missing even though removal coverage had been advanced in the flow; newly created questions did not appear in exam editing because the question list was stale; and deleting a question already linked to an exam left the exam in an invalid state that blocked saving. This required additional corrective prompts and close supervision. | Accepted partially | Useful | The agent worked better for localized edits than for end-to-end completion claims. It followed the staged structure reasonably well, but I still had to manually detect gaps between code, UI behavior, and BDD coverage. A key lesson was that successful build/check results were not enough; manual interaction with the system was necessary to reveal missing functionality and broken flows.
Apply focused corrective fixes to the exams flow: refresh question options when opening exam editing, add minimal exam deletion, and remove broken exam links after question deletion. | This corrective prompt was needed because the previous agent output was not fully reliable in manual validation: exam deletion was still missing, newly created questions were not appearing in exam editing, and deleting a linked question left the exam in an invalid state. | Accepted after correction | Useful with supervision | The agent performed better once the problems were narrowed into explicit corrective tasks. Manual testing was essential to detect gaps that were not visible from build/check results alone.
You are working on a university assignment repository. Repository context: - React + TypeScript client in `sistema/client` - Node + TypeScript server in `sistema/server` - Gherkin/Cucumber scenarios in `sistema/features` - The exams block is already completed and committed - There is repository guidance in `.github/copilot-instructions.md`; follow it Critical product requirement: This block implements requirement 3 of the assignment: generate individual exam PDFs with per-exam variation, header, footer with exam number, student name/CPF area, and a CSV answer key per generated exam. Do not confuse test scaffolding with completed product behavior. Mandatory working mode: Treat this block as a sequence of small internal subparts. Do NOT implement everything in one pass. After each subpart, STOP and explain: 1. what changed 2. which files changed 3. why each changed file was necessary 4. how I can validate locally 5. what remains for the next subparts Critical anti-fake rule: Do not mark a subpart as complete if behavior exists only in Cucumber world, mocks, stubs, fake in-memory file objects, or simulated output. Whenever a subpart is about PDF or CSV generation, the application code must generate a real artifact. Validation rule: Before declaring a subpart complete, you must ensure: - server build passes - server type check passes - the real artifact is generated - you report the exact route, command, or trigger used - you report the exact output path, filename pattern, or response format - you do not change unrelated files Implementation sequence: Subpart 1 — 3A: single PDF generation Goal: - generate one real PDF for one existing exam - no randomization yet - keep current stored order of questions and alternatives Acceptance criteria: - server build passes - server check passes - a real PDF artifact is generated - the PDF is valid and non-empty - current stored order is preserved - no unrelated files are changed Subpart 2 — 3B + 3C: header, footer, student fields Goal: - add exam metadata header - add individual exam number in the footer - add visible space for student name and CPF Acceptance criteria: - previous single-PDF generation still works - header is present - footer with exam number is present - student name/CPF area is present - no unrelated files are changed Subpart 3 — 3D: batch generation Goal: - generate N individual exam PDFs from a provided count - use a real output format such as ZIP if appropriate Acceptance criteria: - batch generation accepts a count - exactly the requested number of real PDFs is produced - no unrelated files are changed Subpart 4 — 3E + 3F: randomization Goal: - randomize question order per generated exam - randomize alternative order per generated exam Acceptance criteria: - generated exams can differ in question order - generated exams can differ in alternative order - answer mapping remains correct for the final randomized output - no unrelated files are changed Subpart 5 — 3G: answer-key CSV Goal: - generate a real CSV artifact for the generated exams - each row contains the exam number and expected answer key Acceptance criteria: - real CSV artifact is generated - rows correspond to generated exams - answer keys match the generated PDFs - no unrelated files are changed Subpart 6 — 3H: Gherkin/Cucumber consolidation Goal: - normalize generation-related feature files - add or update minimal Cucumber support for real implemented behavior only Acceptance criteria: - feature files are aligned with implemented product behavior - no fake generation behavior is treated as completed functionality - no unrelated blocks are changed Important ambiguity to resolve explicitly before coding: The current prepared feature files cover single PDF, layout, batch PDF, and answer-key CSV. They do not explicitly define a randomization scenario yet. Before implementing Subpart 4, propose the minimal feature/scenario adjustment needed for randomization coverage. Strict scope control: - keep each subpart minimal - stop after each subpart - do not continue automatically to the next subpart - do not introduce database persistence - do not redesign the UI - do not broadly refactor unrelated code - do not move into correction/reporting or later blocks Modularity expectation: - keep the slice minimal, but extract a small service/helper when needed for maintainability - avoid forcing PDF/CSV logic into route files - avoid heavy architecture Before editing: 1. summarize the plan for all subparts 2. list likely files per subpart 3. state what will be done in Subpart 1 only 4. mention brief risks 5. state the stop condition explicitly Implementation rule: Start with Subpart 1 only. After finishing Subpart 1, STOP. Do not implement Subparts 2–6 yet. | Implemented real backend endpoints for PDF, batch ZIP, randomization, and answer-key CSV, but did not fully satisfy the product requirements. The generated PDF ignores answerMode in alternative labels, because it always renders A/B/C/D. The name/CPF area was placed near the header instead of at the end of the PDF. No minimal frontend action was added to trigger downloads, which blocked manual validation through the web app. Generation-related .feature files were converted into manual checklist scenarios, so Cucumber is no longer acting as real acceptance coverage for the generation behavior. The CSV export is tied only to the latest in-memory batch, which is a fragile temporary limitation. | Accepted partially | Useful, but required correction prompts | The agent was productive for backend scaffolding and artifact generation, but it drifted from important assignment details. It implemented infrastructure faster than manual coding would, but missed requirement fidelity and weakened the acceptance-test layer. A follow-up correction prompt is needed before considering the block truly finished.
Corrective iteration for block 3: add minimal UI download triggers for PDF/ZIP/CSV and fix PDF labels to respect | The previous generation work had real backend artifact generation, but product validation through the web app was incomplete. There were no minimal frontend triggers for single PDF, batch ZIP with count, or answer-key CSV downloads. The PDF also ignored answerMode when rendering alternatives. This corrective iteration fixed those gaps, but did not resolve the remaining issue that generation-related BDD coverage was still only manual-checklist style rather than executable acceptance coverage. | Accepted partially | Useful, but required correction prompts | The agent corrected an important product-level gap by making generation manually testable through the frontend and by aligning PDF labels with answerMode. This improved real-system validation substantially. However, block 3 should still remain open overall until generation-related Gherkin/Cucumber coverage is converted from manual checklist scaffolding into executable acceptance tests.
Corrective testing iteration for block 3: replace the manual-checklist generation BDD with minimal executable Gherkin/Cucumber acceptance coverage for the real PDF, batch ZIP, CSV, and generation flow. | The current generation-related .feature files and step definitions were consolidated as manual checklists, not as executable acceptance tests. This weakens confidence in block 3 completion because the assignment explicitly requires Gherkin/Cucumber acceptance testing. The next iteration must replace manual-only checklist behavior with real executable validation against actual application behavior, while avoiding fake BDD-world simulation. | Accepted | Useful | This prompt exists because the agent was productive in product implementation but weak in closing the acceptance-test layer. The goal of the next iteration is not new functionality, but trustworthy executable validation for the behavior already implemented in block 3.
Execute Block 4 (grading and report) in controlled internal subparts: 4A answer-key CSV import, 4B student-responses CSV import, 4C strict grading, 4D lenient grading, 4E final report generation, 4F grading-related Gherkin/Cucumber consolidation. Reuse the existing repository scenarios as the acceptance source, reuse the real Block 3 answer-key CSV format if already defined, avoid fake backend-only completion, ensure there is a real way to validate the grading/report flow through the application, and stop after each subpart so I can review, validate, record history, and commit before continuing. | Initial implementation advanced backend/report flow, but Subpart 5 first exposed only report generation in the UI without a real visible path to import CSVs and run grading. Manual correction was needed to make the grading workflow operable through the application. | Accepted partially | Useful, but required correction prompts | The subpart sequence worked and most backend pieces were delivered incrementally, but acceptance was only partial at first because UI validation was incomplete. A correction prompt was required before final acceptance of the visible grading/report flow.
Revise Subpart 5 only. The UI shows a Final Grading Report section and Generate Final Report button, but there is no real visible way in the application to import the answer-key CSV, import the student-responses CSV, and run grading before generating the report. Implement the smallest possible real UI flow for grading/report validation: visible answer-key CSV input, visible student-responses CSV input, grading mode selector, real Run Grading trigger, Generate Final Report working only after grading has run, and simple success/error feedback. Keep the change minimal and reviewable, reuse existing endpoints if possible, and stop after completion explaining validation steps. | The issue targeted by this prompt was the lack of a real UI flow for validation. After correction, the grading workflow became testable directly through the application. | Accepted | Useful | This correction resolved the main acceptance blocker from Subpart 5. The application now exposes a visible grading workflow with answer-key import, student-responses import, run grading, and final report generation, enabling real manual validation from the UI.